## Change Register
Change ID | Regulator | Circular / Act Name | Date Issued | Effective Date | Impact Level | Impact Description | Action Required | Owner | Due Date | Status
FinSecure Pvt Ltd — Regulatory Change Register 2024 ¦ Owner: Compliance Team ¦ Review: Monthly
RC-2026-001 | RBI | RBI Digital Lending Guidelines Amendment — Circular RBI/2025-26/47 | 2026-01-12 | 2026-04-01 | High | Updated digital lending norms — mandatory cooling off period of 3 days for all BNPL products · enhanced borrower grievance mechanism | Update loan product flow · implement cooling off period · revamp grievance portal · retrain customer service team | Compliance & Product Team | 2026-04-01 | In Progress
RC-2026-002 | MeitY | DPDP Act 2023 — Data Protection Board Rules Final Notification 2026 | 2026-02-03 | 2026-02-03 | High | Final DPDP Rules notified — Data Protection Board operational · mandatory breach reporting within 72 hours · DPO registration required · penalty up to INR 250 Crore | Register DPO with Data Protection Board · implement 72-hour breach notification SOP · update privacy notice · train all staff | Legal & DPO | 2026-05-03 | Open
RC-2026-003 | RBI | RBI Guidelines on AI and ML in Financial Services — Final Circular RBI/2025-26/89 | 2026-02-20 | 2026-07-01 | High | Mandatory explainability of AI credit scoring models · bias testing every 6 months · human oversight required for all automated loan decisions above INR 5 lakh · model risk management framework required | Document AI credit model · conduct bias test · implement human review for loans above INR 5L · build model risk framework | Risk & Tech Team | 2026-07-01 | Open
RC-2026-004 | RBI | RBI Cybersecurity Framework for NBFCs — Updated Circular RBI/2025-26/112 | 2026-03-01 | 2026-06-01 | High | Enhanced cyber security requirements for NBFCs — mandatory SIEM implementation · quarterly VAPT · 24x7 SOC · cyber incident reporting within 6 hours | Implement SIEM · schedule quarterly VAPT · explore SOC-as-a-service · update incident response plan | InfoSec Team | 2026-06-01 | Open
RC-2026-005 | RBI | RBI Master Direction — KYC Amendment 2026 — Circular RBI/2025-26/58 | 2026-01-15 | 2026-03-15 | Medium | Periodic KYC update mandatory every 2 years for medium risk customers · Aadhaar based e-KYC preferred over physical documents | Build periodic re-KYC workflow · notify medium risk customers · update onboarding system for Aadhaar e-KYC preference | Compliance Team | 2026-03-15 | In Progress
RC-2026-006 | FIU-IND | FIU-IND Enhanced AML Reporting Requirements 2026 | 2026-01-10 | 2026-04-01 | Medium | New threshold for Cash Transaction Reports lowered to INR 5 lakh · enhanced beneficial ownership disclosure for loan accounts above INR 10 lakh | Update CTR threshold in monitoring system · implement beneficial ownership capture for large loans · retrain compliance team | Compliance & Risk Team | 2026-04-01 | In Progress
RC-2026-007 | SEBI | SEBI Cybersecurity & Cyber Resilience Framework Amendment 2026 | 2026-02-22 | 2026-06-01 | Medium | Updated cyber resilience requirements for entities with SEBI-regulated investment partnerships · mandatory cyber audit annually | Review investment partnership agreements · assess SEBI cyber audit requirement · schedule annual cyber audit | InfoSec & Legal Team | 2026-06-01 | Open
RC-2026-008 | RBI | RBI Interest Rate Transparency Guidelines 2026 — Circular RBI/2025-26/71 | 2026-01-28 | 2026-04-01 | Low | All NBFCs must display effective annualised interest rate (APR) prominently on app and website · no hidden charges | Update app UI to display APR · revise loan offer screen · update website disclosures · legal review of all fee structures | Product & Legal Team | 2026-04-01 | Closed
RC-2026-009 | MeitY | IT Act Amendment — Intermediary Guidelines Update 2026 | 2026-03-05 | 2026-06-05 | Low | Updated intermediary due diligence rules — enhanced grievance officer requirements · faster takedown timelines for harmful content | Appoint updated grievance officer · review content moderation process · update terms of service | Legal Team | 2026-06-05 | Open
RC-2026-010 | RBI | RBI Draft Guidelines on Agentic AI in Financial Services 2026 | 2026-04-01 | TBD — Consultation paper open | High | RBI proposes governance framework for autonomous AI agents in banking — mandatory human oversight · kill switch controls · audit trail for all autonomous decisions · accountability framework | Monitor consultation · assess impact on AI systems · prepare response to RBI consultation · begin agentic AI governance framework | Risk & Tech Team | 30 days post finalisation | Open

## Impact Assessment
FinSecure Pvt Ltd — Regulatory Impact Assessment Template
SECTION 1 — REGULATION DETAILS
Change ID | RC-2026-003 | Regulator | RBI | Date Issued | 2026-02-20
Circular Name | RBI Guidelines on AI and ML in Financial Services — Final Circular RBI/2025-26/89 | Effective Date | 2026-07-01 | Impact Level | High
Summary | RBI mandates explainability of AI credit scoring models · bias testing every 6 months · human oversight required for all automated loan decisions above INR 5 lakh · model risk management framework required
SECTION 2 — IMPACT ANALYSIS
Affected Business Areas | Lending · Credit Underwriting · Technology · Risk Management · Compliance
Affected Policies | Information Security Policy (FS-POL-ISP-001) · AI Risk Framework (to be built) · Data Privacy Policy
Affected Controls | CY-001 (MFA) · CY-002 (VAPT) · CY-005 (SIEM) — existing · New AI-specific controls required
Affected Systems | AI credit scoring model · Loan origination system · Customer decisioning engine
Risk if Non-Compliant | RBI may restrict automated lending operations · impose financial penalty · require manual review of all AI decisions · reputational damage
Estimated Effort | High — requires new AI governance framework · model documentation · bias testing infrastructure · staff training
SECTION 3 — ACTION PLAN
Action # | Action Required | Owner | Priority | Due Date | Status
1 | Document AI credit scoring model — architecture · training data · decision logic · output ranges | Tech Team | Critical | 2026-05-01 | In Progress
2 | Conduct bias testing on AI model — demographic analysis across gender · age · geography · income | Risk Team | Critical | 2026-05-01 | Open
3 | Build explainability layer — generate human-readable reason codes for every automated loan decision | Tech Team | High | 2026-06-01 | Open
4 | Implement human review workflow for all loan decisions above INR 5 lakh | Product Team | High | 2026-06-01 | Open
5 | Build AI Model Risk Management Framework document aligned to RBI guidelines | Risk & Compliance | High | 2026-07-01 | Open
SECTION 4 — APPROVAL & SIGN-OFF
Assessed By | ____________ | Date | ____________
Reviewed By | ____________ | Date | ____________
Approved By | CRO — FinSecure Pvt Ltd | Date | ____________
Next Review Date | 30 days after all actions are closed

## SLA Dashboard
FinSecure Pvt Ltd — Regulatory Change SLA Dashboard 2026
As of April 2026 ¦ SLA: High = 30 days · Medium = 60 days · Low = 90 days ¦ Owner: Compliance Team
OVERALL SUMMARY
Total Changes | Open | In Progress | Closed | Overdue | Compliance %
10 | 5 | 3 | 2 | 0 | 100%
STATUS BY IMPACT LEVEL
Impact Level | Total | Open | In Progress | Closed | SLA Target
🔴 High | 5 | 3 | 1 | 1 | 30 days
🟠 Medium | 3 | 1 | 2 | 0 | 60 days
🟢 Low | 2 | 1 | 0 | 1 | 90 days
TOTAL | 10 | 5 | 3 | 2 | —
STATUS BY REGULATOR
Regulator | Total Changes | Open | In Progress | Closed | Notes
RBI | 6 | 4 | 1 | 1 | 4 high impact items require urgent action
MeitY | 2 | 1 | 1 | 0 | DPDP Rules finalised — DPO registration urgent
FIU-IND | 1 | 0 | 1 | 0 | CTR threshold update in progress
SEBI | 1 | 1 | 0 | 0 | Investment partnership review pending
⚠️ UPCOMING DEADLINES — NEXT 90 DAYS
Change ID | Circular Name | Impact | Due Date | Owner | Status
RC-2026-001 | RBI Digital Lending Guidelines Amendment | High | 2026-04-01 | Compliance & Product | In Progress
RC-2026-002 | DPDP Act — Data Protection Board Rules | High | 2026-05-03 | Legal & DPO | Open
RC-2026-005 | RBI KYC Amendment 2026 | Medium | 2026-03-15 | Compliance Team | In Progress
RC-2026-006 | FIU-IND Enhanced AML Reporting | Medium | 2026-04-01 | Compliance & Risk | In Progress
RC-2026-004 | RBI Cybersecurity Framework for NBFCs | High | 2026-06-01 | InfoSec Team | Open
SLA GUIDE
🔴 High Impact |  | 30 days from effective date |  | CISO + CRO approval required
🟠 Medium Impact |  | 60 days from effective date |  | Compliance Head approval
🟢 Low Impact |  | 90 days from effective date |  | Compliance team sign-off
⏰ Overdue |  | Past due date — not closed |  | Immediate escalation to CRO